## WBS Diagram
WORK BREAKDOWN STRUCTURE DIAGRAM
TITLE | Assignment 1 |  |  | Subject | FIT 2099 OOD
Creator | MD Irfan Chowdhury & Mark Dhruba Sikder |  |  | DATE | 2017-04-28
Assignment 1
PHASE
|  | PREPERATION | PLANNING | DEVELOPMENT |  | FINAL PREP
TASK
|  | Getting The Resources | Opening Github account | Creating New classess |  | Checking all the UML
|  | Checking the codes | Analysing the code | Updating the UML |  | Fixing the error
|  | Running the java project | Dividing the tasks | Creating UML for new class |  | Modifying the tasks required
|  | Checking the UML | Analyzing the UML | Creating relations |  | Submission
|  | Understanding Tasks | Drafting the UML | Creating Sequence Diagram
Work BreakDown
|  | TASK NAME | MARK DHRUBA SIKDER | MD IRFAN CHOWDHURY |  | Date
|  | Creating New Class | Force,Train | LightSabre,Droid,Heal |  | 2017-04-22
|  | Updating The UML | Increased functionality | added new classess in main UML |  | 2017-04-23
|  | Creating UML for new Class | Force,Train | LightSabre,Droid,Heal |  | 2017-04-25
|  | Creating relations | increased work relationship | added methods for new functions |  | 2017-04-25
|  | Creating Sequence Diagram | drafted | created the diagram |  | 2017-04-27
|  | Documentation | Done | Finalised |  | 2017-04-28
|  | Other Tasks | Together | Together